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[bookmark: _Toc67397012][bookmark: _Hlk25143773]C1.1 Form of Offer and Acceptance

[bookmark: _Toc67397013][bookmark: _Hlk25143816]Offer

The Client, identified in the Acceptance signature block, has solicited offers to enter into a contract for the procurement of:

	Turnkey Office Space Planning, Interior Design, Renovations Furniture Procurement Installations Of Utility Infrastructure



The tenderer, identified in the Offer signature block, has examined the documents listed in the Tender Data and addenda thereto and by submitting this Offer has accepted the Conditions of Tender[footnoteRef:2]. [2:  Conditions of Tender are those included in SANS 10845-3 2015 available from https://store.sabs.co.za ] 


By the representative of the tenderer, deemed to be duly authorised, signing this part of this Form of Offer and Acceptance the tenderer offers to perform all of the obligations and liabilities of the Contractor under the contract including compliance with all its terms and conditions according to their true intent and meaning for an amount to be determined in accordance with the conditions of contract identified in the Contract Data. 

	Option A
	The offered total of the Prices exclusive of VAT is 
	
	TBC

	
	Value Added Tax @ 15% is
	
	

	
	The offered total of the Prices inclusive of VAT is[footnoteRef:3] [3:  This total is required by the Client for budgeting purposes only.  Actual amounts due will be assessed in terms of the conditions of contract.] 

	
	

	
	(in words) 
	



This Offer may be accepted by the Client by signing the Acceptance part of this Form of Offer and Acceptance and returning one copy of this document including the Schedule of Deviations (if any) to the tenderer before the end of the period of validity stated in the Tender Data, or other period as agreed, whereupon the tenderer becomes the party named as the Contractor in the conditions of contract identified in the Contract Data.

	Signature(s)

	
	
	

	Name(s)

	
	
	

	Capacity

	
	
	

	For the tenderer:

	(Insert name and address of organisation)

	
Name & signature of witness
	
	
	

Date
	



[bookmark: _Toc67397014]
Acceptance

By signing this part of this Form of Offer and Acceptance, the Client identified below accepts the tenderer’s Offer.  In consideration thereof, the Client shall pay the Contractor the amount due in accordance with the conditions of contract identified in the Contract Data.  Acceptance of the tenderer’s Offer shall form an agreement between the Client and the tenderer upon the terms and conditions contained in this agreement and in the contract that is the subject of this agreement.

The terms of the contract, are contained in: 

Part C1		Agreements and Contract Data, (which includes this Form of Offer and Acceptance)

Part C2		Pricing Data

Part C3		Scope of Work 

Part C4 		Site Information

and drawings and documents (or parts thereof), which may be incorporated by reference into the above listed Parts.

Deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Returnable Schedules as well as any changes to the terms of the Offer agreed by the tenderer and the Client during this process of offer and acceptance, are contained in the Schedule of Deviations attached to and forming part of this Form of Offer and Acceptance.  No amendments to or deviations from said documents are valid unless contained in this Schedule.

The tenderer shall within two weeks of receiving a completed copy of this agreement, including the Schedule of Deviations (if any), contact the Client’s agent (whose details are given in the Contract Data) to arrange the delivery of any securities, bonds, guarantees, proof of insurance and any other documentation to be provided in terms of the conditions of contract identified in the Contract Data at, or just after, the date this agreement comes into effect.  Failure to fulfil any of these obligations in accordance with those terms shall constitute a repudiation of this agreement.

Notwithstanding anything contained herein, this agreement comes into effect on the date when the tenderer receives one fully completed original copy of this document, including the Schedule of Deviations (if any).  

Unless the tenderer (now Contractor) within five working days of the date of such receipt notifies the Client in writing of any reason why it cannot accept the contents of this agreement, this agreement shall constitute a binding contract between the Parties.

	Signature(s)

	
	
	

	Name(s)
	Xolani Zwane

	
	

	Capacity

	Utility Engineer
	
	

	for the Client

	South African National Energy Development Institute (SANEDI)
Block C, Upper Grayston Office Park
152 Ann Crescent
Strathavon
Sandton
2149

	
Name & signature of witness
	
	
	

Date
	



Note: If a tenderer wishes to submit alternative tenders, use another copy of this Form of Offer and Acceptance.
[bookmark: _Toc67397015]
Schedule of Deviations to be completed by the Client prior to contract award

Note:
1. This part of the Offer & Acceptance would not be required if the contract has been developed by negotiation between the Parties and is not the result of a process of competitive tendering.
2. The extent of deviations from the tender documents issued by the Client prior to the tender closing date is limited to those permitted in terms of the Conditions of Tender.
3. A tenderer’s covering letter must not be included in the final contract document.  Should any matter in such letter, which constitutes a deviation as aforesaid be the subject of agreement reached during the process of Offer and Acceptance, the outcome of such agreement shall be recorded here and the final draft of the contract documents shall be revised to incorporate the effect of it.  Insert particulars in place of this symbol and delete rows not required.

	No.
	Subject
	Details

	1
	
	

	2
	
	

	3
	
	

	4
	
	

	5
	
	

	6
	
	

	7
	
	

	
	
	



By the duly authorised representatives signing this Schedule of Deviations below, the Client and the tenderer agree to and accept this Schedule of Deviations as the only deviations from and amendments to the documents listed in the Tender Data and any addenda thereto listed in the Tender Schedules, as well as any confirmation, clarification or changes to the terms of the Offer agreed by the tenderer and the Client during this process of Offer and Acceptance.  

It is expressly agreed that no other matter whether in writing, oral communication or implied during the period between the issue of the tender documents and the receipt by the tenderer of a completed signed copy of this Form shall have any meaning or effect in the contract between the parties arising from this Agreement. 

	
	For the tenderer:
	
	For the Client

	Signature

	
	
	

	Name
	

	
	Xolani Zwane

	Capacity

	
	
	Utility Engineer

	On behalf of
	(Insert name and address of organisation)



	
	South African National Energy Development Institute (SANEDI)
Block C, Upper Grayston Office Park
152 Ann Crescent
Strathavon
Sandton
2149

	Name & signature of witness
	
	
	

	
Date
	
	
	






[bookmark: _Toc67397016]C1.2 ECC4 Contract Data

[bookmark: _Toc67397017]Part one - Data provided by the Client

	Data for the Core Clauses

	Clause number
	Identified statement and data



	11.1
	The conditions of contract are the core clauses and the clauses for the following main Option, the Option for resolving and avoiding disputes and secondary Options of the NEC4 Engineering and Construction Contract, June 2017 with amendments October 2020.

	
	Main Option
	ECC4 Option A – Fixed Price with Activity Schedule

	
	Option for resolving and avoiding disputes
	W1

	
	Secondary Options
	X2 - Changes in the law

	
	
	X5 – Sectional Completion

	
	
	X7 – Delay Damages

	
	
	X8 – Undertakings to the Client and Others

	
	
	X9 – Transfer of rights

	
	
	X11 – Termination by Client

	
	
	X13 - Performance bond

	
	
	X18 - Limitation of Liability

	
	
	Z: Additional conditions of contract



	11.2(15)
	The works are
	The turnkey refurbishment and fit-out of SANEDI's leased office floor at Upper Grayston Block B, including design development, landlord approvals, demolition, fit-out, services modifications, FF&E, coordination with the separate ICT contractor, testing, commissioning, handover and defects correction as described in the Scope.



	10.1
	The Client is
	

	
		Name
	
	South African National Energy Development Institute (SANEDI)

A state-owned entity established under Section 7 of the National Energy Act 43 of 2008.

	
		Address for communications
	Block C, Upper Grayston Office Park
152 Ann Crescent
Strathavon
Sandton
2149

	
		Address for electronic communications
	XolaniZ@sanedi.org.za



	10.1
	The Project Manager is
	

	
		Name
	Xolani Zwane

	
		Address for communications
	Block C, Upper Grayston Office Park
152 Ann Crescent
Strathavon
Sandton
2149

	
		Address for electronic communications
	XolaniZ@sanedi.org.za



	10.1
	The Supervisor is
	

	
		Name
	TBC

	
		Address for communications
	


	
		Address for electronic communications 
	



	11.2(16)
	The Scope is in
	Part 3: Scope of Work and all documents and drawings to which it refers.



	11.2(18)
	The Site Information is in
	Part 4: Site Information and all documents and drawings to which it refers.



	11.2(17)
	The boundaries of the site are
	The boundaries of the Site are the leased office floor refurbishment area at Upper Grayston Block B as defined in the high-level design drawings, Site Information and landlord-approved fit-out boundary, including only those ancillary areas expressly stated in the Scope and annexures.



	13.1
	The language of the contract is
	English



	12.2
	The law of the contract is the law of
	the Republic of South Africa



	13.3
	The period for reply is
	1 week
	



	15.2
	The following matters will be included in the Early Warning Register

	
	· Landlord approval requirements; 
· Noise, vibration, dust or disruption affecting the wellness centre, doctor, patients, staff, visitors, landlord, SANEDI or other building users;
· Existing HVAC status; 
· Base building services interfaces; 
· Equipment lead times; 
· Statutory approvals.



	15.2
	Early warning meetings are to be held at intervals no longer than
	2 week







	25.3
	The key dates and conditions to be met are:
	

	
	condition to be met
	key date

	(1)
	N/A
	



	31.2
	The starting date is
	
	TBC



	30.1
	The access dates are:
	
	

	
	part of the Site
	date

	(1)
	Whole Site
	TBC

	(2)
	
	

	(3)
	
	



	32.2
	The Contractor submits revised programmes at intervals no longer than
	

	
	
	2 weeks




	11.2(2) & 11.2(3)
	The completion date for the whole of the works is
	TBC – 30 November 2026




	35.1 
	The Client 
willing to take over the works before the Completion Date.  
	is




	31.1
	The period after the Contract Date within which the Contractor is to submit a first programme for acceptance is
	

	
	
	2 weeks



	40.2
	The period after the Contract Date within which the Contractor is to submit a quality

	
	policy statement and quality plan is
	2 weeks



	43.1 & 43.2
	The period between Completion of the whole of the works and the defects date is
	26 weeks



	44.2
	The defect correction period is
	 1 week
	





	51.1
	The currency of the contract is the
	ZAR



	50.1
	The assessment interval is
	4 weeks



	51.4
	The interest rate is
	 2% per annum
	 above the

	
	 Prime
	rate of the
	Standard Bank of South Africa
	(bank)



	51.2
	The period within which payments are made is
	30 days



	60.1(13)
	The place where weather is to be recorded is
	Sandton, Johannesburg



	60.1(13)
	The weather measurements to be recorded for each calendar month are

	
	· the cumulative rainfall (mm)

	
	· the number of days with rainfall more than 10 mm

	
	· the number of days with minimum air temperature less than 0 degrees Celsius

	
	· the number of days with snow lying at 09:00 hours South African Time

	
	and these measurements

	
	N/A


	
	The weather measurements are supplied by
	Client




	60.1(13)
	The weather data are the records of past weather measurements for each calendar month 

	
	which were recorded at
	SAWS station information lists JHB BOT TUINE, station number 68361, at coordinates -26.1566, 27.9991

	
	and which are available from:
	the South African Weather Services.



	60.1(13)
	Where no recorded data are available, assumed values for the ten-year return weather data for each weather measurement for each calendar month are:

	
	stated in Annexure A to this Contract Data provided by the Client.








	80.1
	These are additional Client's liabilities
	

	(1)
	N/A

	(2)
	

	(3)
	



	83.3 Insurance Table row 3
	The minimum amount of cover for insurance against loss of or damage to property (except the works, Plant, Materials and Equipment) and liability for bodily injury to or death of a person (not an employee of the Contractor) arising from or in connection with the Contractor Providing the Works for any one event is: 

	
	Contractors’ All Risks policy at contract value plus VAT



	83.3 Insurance Table row 4
	The minimum amount of cover for insurance against death of or bodily injury to employees of the Contractor arising out of and in the course of their employment in connection with the contract for any one event is:

	
	as prescribed by the Compensation for Occupational Injuries and Diseases Act No. 130 of 1993 and the Contractor’s common law liability for people falling outside the scope of the Act with a limit of cover of not less than R 10 million (Rands).




	83.1
	The Client provides these insurances from the Insurance Table

	
	(1) Insurance against
	Nil

	
	Minimum amount of cover is
	

	
	The deductibles are
	




	83.1
	The Client provides these additional insurances

	
	(1) Insurance against
	Nil

	
	Minimum amount of cover is
	.

	
	The deductibles are
	 



	83.2
	The Contractor provides these additional insurances

	
	(1) Insurance against
	Furniture and Equipment insurance until project completion and handover

	
	Minimum amount of cover is
	Value of equipment as shown in the Activity Schedule

	
	The deductibles are
	N/A

	
	
	






	Data for the main Option A



	Clause number
	Identified statement and data



Data for Option A Priced contract with activity schedule

	63.12
	The value engineering percentage is 50%, unless another percentage is stated here, in which case it is 
	

	
	
	N/A
	%



Data for resolving and avoiding disputes.

	W1.4(1), and W3.3(1)
	The tribunal is
	arbitration

	W1.4(5), and W3.3(4)
	The arbitration procedure is
	the latest edition of Rules for the Conduct of Arbitrations published by The Association of Arbitrators (Southern Africa) or its successor body.

	W1.4(5)
	The place where arbitration is to be held is
	 Johannesburg, South Africa

	W1.4(5)
	The person or organisation who will choose an arbitrator if the Parties cannot agree a choice or if the arbitration procedure does not state who selects an arbitrator, is

	
	the Chairman for the time being or his nominee of the Association of Arbitrators (Southern Africa) or its successor body.




If Option W1 is used
	W1.1(1)
	The Senior Representatives of the Client are

	
	Name (1)
	Tebogo Snyer

	
	Address for communications
	Block C, Upper Grayston Office Park, 152 Ann Crescent, Strathavon, Sandton, 2146

	
	Address for electronic communications
	TebogoS@sanedi.org.za

	
	Name (2)
	TBC

	
	Address for communications
	


	
	Address for electronic communications
	



	W1.2
	The Adjudicator is (Name)
[It is always preferable to name the Adjudicator at time of award. If this can be done delete this data and insert the name and contact details below.] 

	the person selected from the ICE-SA Division (or its successor body) of the South African Institution of Civil Engineering Panel of Adjudicators by the Party intending to refer a dispute to him.  (see www.ice-sa.org.za

	
	Address for communications
	


	
	Address for electronic communications
	

	
	The Adjudicator nominating body is:
	the Chairman of ICE-SA a joint Division of the South African Institution of Civil Engineering and the London Institution of Civil Engineers. (See www.ice-sa.org.za ) or its successor body.




	Data for the secondary Option clauses



	Clause number
	Identified statement and data



X2: Changes in the law
	
	There is no reference to Contract Data in this Option 



X5: Sectional Completion
	11.2(3) & X5.1
	The completion date for each section of the works is

	
	section
	description
	completion date

	
	(1) 
	Design submission from Contractor
	4 weeks from Starting Date

	
	(2)
	
	

	
	(3)
	
	

	
	(4)
	
	

	
	
	
	



X7: Delay damages if Option X7 is used together with Option X5
	X7.1 & 11.2(3)
	Delay damages for Completion of the whole of the works are 
	1%  to a maximum of 10% of the Contract Value
	per day



	
	Delay damages for each section of the works are 
	

	
	section
	description
	amount per day

	
	(1)
	Design submitted by Contractor
	R 35 000.00

	
	(2)
	
	R 

	
	(3)
	
	R 




X8: Undertakings to the Client or Others
	X8.1
	The undertakings to Others are 

	
	provided to:
	

	
	The Landlord
	

	
	
	

	X8.2
	The Subcontractor undertaking to Others are

	
	works
	provided to

	
	HVAC
	The Landlord

	
	Other systems
	The Landlord

	X8.3
	The Subcontractor undertaking to the Client are

	
	works
	

	
	TBC
	

	
	
	




X9: Transfer of rights
	
	There is no reference to Contract Data in this Option.




X11: Termination by the Client
	
	There is no reference to Contract Data in this Option 



X13: Performance bond
	X13.1
	The amount of the performance bond is 
	5% of Contract Value




X18: Limitation of liability
	X18.5
	The Contractor’s total liability to the Client for all matters arising under or in connection with this contract, other than excluded matters, is limited to:
	

	
	
	100% of the Total of the Prices at Contract Date

	X18.6
	The end of liability date is
	1
	years after Completion of the whole of the works




Z: Additional conditions of contract 
	
	The additional conditions of contract are
	Z1
	Payment (Clause 51)

	
	Add a new Clause 51.6 to core clause 51:

The Contractor (if registered in South Africa in terms of the Companies Act) is required to comply with the requirements of the Value Added Tax Act, no 89 of 1991 (as amended) on each invoice that the Contractor submits for payment.


	Z2
	Notifying compensation events (Clause 61)

	
	Delete “eight weeks” in clause 61.3 and replace with “two weeks”.


	Z3
	Client’s risks (Clause 81.1):

	
	Add the following to clause 81.1:

The following are expressly not Client’s risks:

Electricity failures due to Load-shedding or Cable theft;
Strikes by the Contractor’s own personnel; and
Slow or interrupted Data / Wi-Fi / Fibre lines.

The Contractor will remain liable to mitigate the impact of delay events.


	Z4
	Payment on Termination (Clause 92)

	
	Add a new clause 92.3: 
 
Consequence of Termination:  Return of documents and Assignment on Termination- 

In the event of early termination of the Contract the Contractor shall immediately upon receipt of the notice of termination:

refund any upfront payments received (save for annual licence fees paid in advance)
return all Client’s property to the Client;
deliver all Contractor's documents and work-in-progress to the Client;
provide all designs, drawings, material, equipment anything else required to enable the Client to beneficially use the Works paid for;
return all relied upon and issued information to the Client;
on the request of the Client assign all existing Subcontracts and transfer Contractor’s work in progress to the Client; and
return all Confidential Information to the Client.


	Z5
	Ethical Compliance

	
	Core Clause 11.2 (5) and 17.1 – 17.3 is supplemented by the following inclusion:

The Client is committed to the highest standards of honesty, integrity and fairness  and has a zero tolerance for the commissioning or concealment of fraudulent acts by the Contractor, employees, tenderers or suppliers.

Any act or consideration of any kind as an inducement or reward for doing or refraining from doing, in relation to the obtaining or execution of a tender or contract by Contractors or  Tenderers will be viewed as a fraudulent act.

The Contractor undertakes to comply with the Corruption and Economic Crime Act of 1994, the Amended Corruption and Economic Crime Act of 2003, Proceeds and Instruments of Crime of 2014 and other similar applicable laws in any other jurisdictions.

	Z6
	B-BBEE Requirements

	
	B-BBEE shall refer to the Broad-Based Black Economic Empowerment (B-BBEE) Codes of Good Practice issued by the Minister of Trade and Industry in the Country.

The Contractor may be required during the tender and / or thereafter to submit it and maintain its B-BBEE contributor level achieved in terms of the Department of Trade and Industry Codes of Good Practice on B-BBEE, as at the signature date of this Contract, and for the duration of the Contract.

When so requested, the Contractor shall provide the Client with a valid B-BBEE verification certificate from a rating agency accredited by the South African National Accreditation Service, reflecting the Contractor’s Contributor Level.

The Contractor shall maintain or improve its Contributor Level for the duration of this Contract in accordance with the Codes of Good Practice on Black Economic Empowerment, issued in terms of section 9(1) of the B-BBEE Act, as amended from time to time; and

Notify the Client in writing within 10 Business Days of the occurrence of any event which affects, will affect, or would reasonably likely affect its Contributor Level and the steps it proposes will be taken to restore and/or improve its B-BBEE Contributor Level.

Any failure by the Contractor to comply with the provisions of this clause shall be a material breach of this Contract and the Client shall be entitled, without prejudice to any other rights which it may have in law, to terminate this Contract with immediate effect.


	Z7
	Cession Assignment and Delegation of Rights and Liabilities

	
	The Contractor hereto may not cede, assign or delegate any of its rights and/or obligations (including liabilities) under this Contract to any person without the prior written consent of the Client.

The Client’s consent to any such assignment, cession or delegation, if given, shall not relieve the Contractor from any liability or obligation under the contract and the Contractor shall be liable for any loss, damage or injury arising out of any act or omission of such Subcontractor, its agents or servants as fully as if such loss, damage or injury resulted from the act or omission of the Contractor his servants or agents.

Notwithstanding the above, the Client may give notice to the Contractor to cede, assign and delegate its rights and/or obligations under this contract to any of its subsidiaries or any of its present divisions or operations which are separate legal entities.

	Z8
	Confidentiality of Documentation 

	
	The Contractor shall treat as strictly secret and confidential all information of whatsoever nature and in whatsoever nature and in whatsoever format relating to the operations and business of the Client, it being agreed and undertaken by the Contractor that such information is not to be disclosed, directly or indirectly to any person without the prior written consent of the Client or in terms of any order of a Court of competent jurisdiction which shall have directed it, or as may be required by law or by the rules of any recognised stock exchange.

The Contractor shall take or cause to be taken such reasonable precautions as may be necessary to prevent the disclosure of any such information which is not a matter of public knowledge or lawfully available from any other source.

The Contractor shall not, without the prior written consent of the Client, take or permit to be taken any photographs or other images of the Client’s property or any portion thereof, display any advertisements in connection with the contract, or publish, cause or permit to be published any article, story or other material having any references whatsoever to the contract.


	Z9
	Contractor’s Lien

	
	The Contractor hereby waives and abandons the Contractor’s lien and/or any other right of retention which the Contractor now has or in future may have, in terms of the Contract, the common law or otherwise, in respect of the services, deliverables or any property of the Client. The Contractor warrants that all subcontractors, mutatis mutandis, shall waive and abandon any such subcontractor’s lien or any other right of retention.


	Z10
	Protection of Personal Information Act 4 of 2013(POPIA) 

	
	The Party(ies) undertake(s) to comply with the provisions of POPIA as well as all applicable legislation as amended or substituted from time to time; and treat all Personal Information strictly as defined within the parameters of POPI.  


	Z11
	Contract documents and order of precedence

	
	The Contract is the NEC4 Engineering and Construction Contract as amended by these additional conditions of contract, the Contract Data, the Scope, the Site Information, the Activity Schedule and the documents identified in the Contract Data.

The SANEDI Standard Conditions of Contract, General Conditions of Contract, bid conditions, tender returnables and the Contractor’s tender submission apply only to the extent that they are expressly incorporated into this Contract and are not inconsistent with the NEC4 Engineering and Construction Contract as amended by these additional conditions.

If there is any conflict or inconsistency between the NEC4 Engineering and Construction Contract and any SANEDI Standard Conditions of Contract, General Conditions of Contract, tender condition, tender returnable, quotation, proposal or supplier condition, the NEC4 Engineering and Construction Contract as amended by these additional conditions prevails.

No terms or conditions proposed by the Contractor in its quotation, proposal, invoice, delivery note or correspondence apply unless expressly accepted in writing by the Project Manager and incorporated into the Contract.










[bookmark: _Toc67397018]Annexure A: One-in-ten-year-return weather data 

Obtained from SA Weather Bureau for __TBC_____ weather station.

If any one of these weather measurements recorded within a calendar month, before the Completion Date for the whole of the works and at the place stated in this Contract Data is shown to be more adverse than the amount stated below, then the Contractor may notify a compensation event.



	
	Weather measurement

	Month
	Cumulative rainfall (mm)
	Number of days with rain more than 10mm
	Number of days with min air temp < 0 deg.C
	Number of days with snow lying at 08:00 CAT
	[Other measurements if applicable]

	January
	125.0
	4.5
	0.0
	0.0
	

	February
	90.0
	3.2
	0.0
	0.0
	

	March
	91.0
	3.0
	0.0
	0.0
	

	April
	54.0
	1.8
	0.0
	0.0
	

	May
	13.0
	0.5
	0.2
	0.0
	

	June
	9.0
	0.2
	1.1
	0.0
	

	July
	4.0
	0.1
	1.3
	0.0
	

	August
	6.0
	0.2
	0.4
	0.0
	

	September
	27.0
	0.9
	0.0
	0.0
	

	October
	72.0
	2.5
	0.0
	0.0
	

	November
	117.0
	4.1
	0.0
	0.0
	

	December
	105.0
	3.8
	0.0
	0.0
	







Only the difference between the more adverse recorded weather and the equivalent measurement given above is taken into account in assessing a compensation event.





[bookmark: _Toc67397019]Part 2 – Data provided by the Contractor.


	Data for the Core Clauses

	Clause number
	Identified statement and data

	10.1
	The Contractor is
	

	
		Name
	
	

	
		Address for communications
	


	
		Address for electronic communications
	




	11.2(10) & 52.1
	The fee percentage is 
	
	%



	11.2(20) &16.3
	The working areas are the Site and
	

	
	
	

	24.1
	The key persons are 
	

	
		Name (1)
	

	
		Job
	

	
		Responsibilities
	

	
		Qualifications
	

	
		Experience
	

	
	
	

	
		Name (2)
	

	
		Job
	

	
		Responsibilities
	

	
		Qualifications
	

	
		Experience
	

	
	
	

	11.2(8)
	The following matters will be included in the Early Warning Register:

	
	







	11.2(16) and 21.1
	The Scope provided by the Contractor for its design is in
	




	31.1
	The programme identified in Contract Data is
	




	11.2(3)
	The completion date for the whole of the works
	





	Data for the main Option A



	Clause number
	Identified statement and data



Option A priced contract with activity schedule 
	11.2(21)
	The activity schedule is in
	



	
	The tendered total of the Prices excluding VAT is
	




[bookmark: _Hlk22650555]Data for resolving and avoiding disputes.

Option W1
	W1.1(1)
	The Senior Representatives of the Contractor are 

	 
		Name (1)
	

	
		Address for communications
	


	
	Address for electronic communications
	

	
	
	

	
		Name (2)
	

	
		Address for communications
	


	
	Address for electronic communications
	



Data for Short Schedule of Cost Components

	11.2(28) and SSCC 11
	The people rates are

	
	Category of person
	unit
	rate

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	



	SSCC 21
	The published list of Equipment is the edition current at the Contract Date of the list published by
	

	
	The percentage for adjustment for Equipment in the published list is 
	
	% (state plus or minus)



	SSCC 22
	The rates for other Equipment are

	
	Equipment
	rate
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	



	SSCC 61
	The rates for Defined Cost of manufacture and fabrication outside the Working Areas by the Contractor are

	
	Category of person
	rate
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	



	SSCC 71
	The rates for Defined Cost of design outside the Working Areas are

	
	Category of person
	rate
	

	
	
	
	

	
	
	
	

	
	
	
	

	
	
	
	



	SSCC 72
	The categories of design people whose travelling expenses to and from the Working Areas are included in Defined Cost are

	
	









[bookmark: _Hlk25315368]C1.3 Forms of Securities 


Pro forma Performance Bond – Demand Guarantee
(to be reproduced exactly as shown below on the letterhead of the Bank providing the Guarantee)

	Client’s name and address
	Reference No.



Date:
	_______  [ Bank reference number to be inserted]



Dear Sirs,

Performance Bond – Demand Guarantee for [insert name of Contractor] required in terms of contract [insert Contractor’s contract reference number or title]

1. In this Guarantee the following words and expressions shall have the following meanings: -

	1.1
	“Bank” means
	[Insert name of Bank], _______  Branch, Registration No. _______ 

	1.2
	“Bank’s Address” means
	[Insert physical address of Bank]

	1.3
	“Contract” means
	the written agreement relating to the project works, entered into between the Client and the Contractor, on or about the _______  day of _______  20_______  (Contract Reference No. _______ ) as amended, varied, restated, novated or substituted from time to time; 

	1.4
	“Contractor” means
	_______  a company registered in accordance with the laws of _______  under Registration No _______ .

	1.5
	“Client” means
	_______  a company registered in accordance with the laws of the Republic of South Africa under Registration Number _______ 

	1.6
	“Expiry Date” means
	the date on which the Defects Certificate (as defined in the Contract) is due to be issued in terms of the Contract. 

	1.7
	“Guaranteed Sum” means
	the sum of R_______ , (_______  Rand)

	1.8
	“Project” means
	_______ 



2. At the instance of the Contractor, we the undersigned ______________ and ______________, in our respective capacities as _____________ and ___________ of the Bank, and duly authorized thereto, confirm that we hold the Guaranteed Sum at the disposal of the Client as security for the proper performance by the Contractor of all of its obligations in terms of and arising from the Contract and hereby undertake to pay to the Client, on written demand from the Client received prior to the Expiry Date, any sum or sums not exceeding in total the Guaranteed Sum.

3. A demand for payment under this guarantee shall be made in writing at the Bank’s address and shall:

· be signed on behalf of the Client by a director of the Client;
· state the amount claimed (“the Demand Amount’);
· state that the Demand Amount is payable to the Client in the circumstances contemplated in the Contract.

4. Notwithstanding the reference herein to the Contract the liability of the Bank in terms hereof is as principal and not as surety and the Bank’s obligation/s to make payment:

· is and shall be absolute provided demand is made in terms of this bond in all circumstances; and
· is not, and shall not be construed to be, accessory or collateral on any basis whatsoever. 

5. The Bank’s obligations in terms of this Guarantee:

· shall be restricted to the payment of money only and shall be limited to the maximum of the Guaranteed Sum; and
· shall not be discharged and compliance with any demand for payment received by the Bank in terms hereof shall not be delayed, by the fact that a dispute may exist between the Client and the Contractor.

6. The Client shall be entitled to arrange its affairs with the Contractor in any manner which it sees fit, without advising us and without affecting our liability under this Guarantee. This includes, without limitation, any extensions, indulgences, release or compromise granted to the Contractor or any variation under or to the Contract. 

7. Should the Client cede its rights against the Contractor to a third party where such cession is permitted under the Contract, then the Client shall be entitled to cede to such third party the rights of the Client under this Guarantee on written notification to the Bank of such cession.

8. This Guarantee:

· shall expire on the Expiry Date until which time it is irrevocable;
· is, save as provided for in 7 above, personal to the Client and is neither negotiable nor transferable;
· shall be returned to the Bank upon the earlier of payment of the full Guaranteed Sum or expiry hereof;
· shall be regarded as a liquid document for the purpose of obtaining a court order; and
· shall be governed by and construed in accordance with the law of the Republic of South Africa and shall be subject to the jurisdiction of the Courts of the Republic of South Africa. 
· will be invalid and unenforceable if any claim which arises or demand for payment is received after the Expiry Date.

9. The Bank chooses domicilium citandi et executandi for all purposes in connection with this Guarantee at the Bank’s Address.

	Signed at
	
	on this
	
	day of 
	
	20__



For and on behalf of the Bank

	Bank Signatories(s)
	

	

	Name(s) (printed)
	
	

	Witness(s)

	
	

	Bank’s seal or stamp
	
	









[bookmark: _Toc67397020]Part C2 Pricing Data

If main Option A is chosen, delete the sections for each of the other Options and delete this note
[bookmark: _Toc67397021]C2.1 Pricing assumptions Option A

[bookmark: _Hlk25143929]How work is priced and assessed for payment

Clause 11 in NEC4 Engineering and Construction Contract, (ECC4) Option A states:

	Identified and defined terms
	11
11.2
	
(21) The Activity Schedule is the activity schedule unless later changed in accordance with this contract.


	
	
	(29) The Price for Work Done to Date is the total of the Prices for 

each group of completed activities and
each completed activity which is not in a group.

A completed activity is one without notified Defects the correction of which will delay following work.


	
	
	(32) The Prices are the lump sum prices for each of the activities on the Activity Schedule unless later changed in accordance with the contract.




This confirms that Option A is a lump sum form of contract where the work is broken down into activities, each of which is priced by the tendering contractor as a lump sum.   Only completed activities are assessed for payment at each assessment date; no part payment is made if the activity is not completed by the assessment date. 

Function of the Activity Schedule

Clause 55.1 in Option A states: “Information in the Activity Schedule is not Scope or Site Information”.  This confirms that specifications and descriptions of the work or any constraints on how it is to be done are not included in the Activity Schedule but in the Scope.  This is further confirmed by Clause 20.1 which states, “The Contractor Provides the Works in accordance with the Scope”. Hence the Contractor does not Provide the Works in accordance with the Activity Schedule.  The Activity Schedule is only a pricing document.  

Link to the programme

Clause 31.4 states that “The Contractor provides information which shows how each activity on the Activity Schedule relates to the operations on each programme submitted for acceptance”.  Ideally the tendering contractor will develop a high level programme first then resource each activity and thus arrive at the lump sum price for that activity both of which can be entered into the activity schedule.  

Preparing the activity schedule

Generally it is the tendering contractor who prepares the activity schedule by breaking down the work described within the Scope into suitable activities which can be well defined, shown on a programme and priced as a lump sum.

The Client, in its Instructions to Tenderers or in a Tender Schedule, may have listed some items that it requires the Contractor to include in its activity schedule and be priced accordingly. 

It is assumed that in preparing its activity schedule the Contractor:

· Has taken account of the guidance given in the “NEC4 User Guide Preparing an Engineering and Construction Contract Volume 2” page 84.
· Understands the function of the Activity Schedule and how work is priced and paid for;
· Is aware of the need to link the Activity Schedule to activities shown on its programme;
· Has listed and priced activities in the activity schedule which are inclusive of everything necessary and incidental to Providing the Works in accordance with the Scope, as it was at the time of tender, as well as correct any Defects not caused by a Clients risk;
· Has priced work he decides not to show as a separate activity within the Prices of other listed activities in order to fulfil the obligation to complete the works for the tendered total of the Prices. 
· Understands there is no adjustment to the lump sum Activity Schedule price if the amount, or quantity, of work within that activity later turns out to be different to that which the Contractor estimated at time of tender. The only basis for a change to the Prices is as a result of a compensation event. 



If main Option A is chosen, delete the sections for each of the other Options and delete this note

[bookmark: _Toc67397022]C2.2 The activity schedule – Option A (DRAFT BELOW – CONTRACTOR TO DEVELOP AS APPLICABLE)

The Activity Schedule is to be prepared by the bidding Contractor. An activity schedule could have the following format (will be agreed prior to contract signing): 

	Item
No.
	Programme Reference
	Activity description
	Price

	1
	P01
	Provision of insurances and performance bond 
	

	2
	P02
	Provision of the project programme, HSE plan and quality plan
	

	3
	P03
	Design development, coordination, samples, approvals by SANEDI, Project Manager and landlord
	

	4
	P04
	Submission of design
	

	5
	P05
	Acceptance of design by Project Manager
	

	6
	P06
	Site establishment
	

	7
	P07
	Pre-construction surveys, condition report, services verification and setting out
	

	8
	P08
	Demolition, strip-out, isolation, removal, disposal and making safe
	

	9
	P09
	Partitions, walls, glazing, doors, ironmongery and screens
	

	10
	P10
	Ceilings, bulkheads, access panels and acoustic treatments
	

	11
	P11
	Flooring, skirtings, wall finishes, painting, branding surfaces and making good
	

	12
	P12
	Joinery, reception, kitchen, tea area, bathroom/ablution works where included, fixtures and fittings
	

	13
	P13
	Electrical power, lighting, emergency lighting, controls, testing and Electrical Certificate of Compliance
	

	14
	P14
	HVAC modifications, controls coordination, balancing, testing and commissioning in accordance with HVAC status annexure
	

	15
	P15
	Fire and life safety works, fire stopping, signage, testing and certificates where applicable
	

	16
	P16
	Security, access control interfaces, signage, wayfinding, manifestation and landlord signage requirements
	

	17
	P17
	Furniture, Fitout and Equipment (FF&E) procurement, delivery, installation, placement and warranties in accordance with FF&E pack
	

	18
	P18
	ICT interface coordination, access, containment/builders work coordination and programme integration
	

	19
	P19
	Testing, commissioning, statutory certificates, snagging, landlord inspection and occupation readiness
	

	20
	P20
	As-built drawings, O&M manuals, warranties, asset schedules, training, final clean and handover
	

	21
	P21
	Defects correction, close-out support and completion of outstanding landlord/SANEDI handover requirements
	







[bookmark: _Toc67397033]Part C3 Scope of Work

[bookmark: _Toc67397034]C3.1: The Client’s scope

S 100 Description of the works

	S 105 Project objectives
	The project objective is to provide SANEDI with a complete, safe, compliant and occupation-ready office refurbishment delivered as a turnkey NEC4 ECC Option A project. The Works provide a functional office fit-out based on the Client's high-level plans and supporting annexures, with final design developed by the Contractor and approved by the Client and landlord before construction. The tender documents use annexures and pricing information so that all tenderers price the same scope and can be evaluated on a comparable basis.

	S 110 Description of the works (general only)
	The Works comprise the turnkey refurbishment and fit-out of SANEDI's leased office floor at Upper Grayston Block B. The Contractor Provides the Works including design development, coordination with the Client, designer, landlord and Others, landlord approvals, demolition and strip-out, internal construction, fit-out, services modifications, FF&E within the Contractor's scope, testing, commissioning, certification, handover and defects correction. ICT is excluded except for the coordination and interface obligations stated in this Scope.



S 200 Constraints on how the Contractor Provides the Works

	S 201 General constraints
	The Contractor complies with the Client's requirements, the landlord requirements and all constraints stated in the Scope, Site Information and annexures. The Contractor allows for access restrictions, working hours, noisy works, deliveries, lift use, common area protection, dust and waste control, security procedures, permits, inductions, statutory requirements and coordination with Others. The Contractor does not alter landlord-controlled common areas, base building services, structure, facade or other tenant areas unless accepted by the Project Manager and approved by the landlord.

	S 210 Confidentiality
	The Contractor keeps confidential all lease, landlord, SANEDI, design, pricing, operational and security information obtained in connection with the Works and uses it only for Providing the Works.

	S 215 Security and protection of the Site
	The Contractor secures the Site, controls access to its working areas, protects the leased premises, common areas, lifts, lobbies, staircases, existing services and all landlord property, and immediately makes safe any unsafe condition created by its operations.

	S 220 Security & identification of people
	All people engaged by the Contractor and its subcontractors comply with landlord and Client security procedures, access control, sign-in requirements, inductions, identification and permit-to-work requirements.

	S 225 Protection of existing structures and services
	The Contractor protects existing structures, finishes, services and base building systems. The Contractor records pre-existing damage in the pre-construction condition survey and is responsible for damage caused by its operations.

	S 230 Protection of the works
	The Contractor protects the Works until Completion, including completed finishes, FF&E, services, signage, glazing, joinery and any ICT installations or interfaces installed by Others while the Contractor remains in the working area.

	S 235 Cleanliness of roads
	The Contractor keeps access routes, loading areas, parking areas, lobbies, corridors, lifts and common areas clean and free from debris, dust and damage caused by the Works.

	S 240 Traffic management
	The Contractor manages deliveries, loading, offloading, parking, waste removal and movement of materials in accordance with landlord requirements and without obstructing other tenants, common areas, emergency routes or building operations.

	S 245 Condition survey
	Before commencing demolition or construction, the Contractor prepares a photographic condition survey recording the condition of the Site, common areas used by the Contractor, existing finishes, existing services, HVAC, electrical, fire, plumbing, access routes, lobbies and lifts. The Contractor submits the survey to the Project Manager.

	S 250 Consideration of Others
	The Contractor is advised that the ground floor of the building is occupied and used as a wellness centre and medical practice. The Contractor Provides the Works in a manner that minimises disruption, noise, vibration, dust, odours, obstruction and interference with the operations of the wellness centre, doctor, patients, staff, visitors, SANEDI, the landlord and other building users.

The Contractor allows in its programme, method statements and Prices for restrictions on noisy works and disruptive activities. Noisy works include demolition, drilling, chasing, cutting, hammering, coring, fixing, grinding, impact tools, service penetrations and any other activity likely to disturb the wellness centre or medical practice.
The Contractor carries out noisy or disruptive works only during times accepted by the Project Manager and approved by the landlord or building management. The landlord will consult with the wellness centre and doctor regarding suitable working periods. The Contractor allows for possible after-hours, weekend or restricted-hours working where required to minimise disruption.

The Contractor gives the Project Manager not less than 5 working days notice before undertaking noisy or disruptive works. The notice identifies the nature of the work, expected duration, affected areas, proposed mitigation measures and any access or service interruptions required.

The Contractor’s Accepted Programme shows the timing of noisy works, restricted activities, landlord approval periods and any agreed after-hours or weekend work. The Contractor updates the programme when working-time restrictions are confirmed or changed.
The Contractor is not entitled to cause avoidable disruption to the wellness centre, doctor, patients, staff, visitors, SANEDI or the landlord’s operations.

	S 255 Industrial relations
	The Contractor manages labour relations and conduct of its workforce so that there is no disruption to SANEDI, the landlord, building users, other tenants or the public.

	S 260 Control of works
	The Contractor plans, manages and controls the Works using competent supervision, accepted programmes, method statements, inspection and test plans, quality controls and safe working procedures.

	S 265 Site cleanliness
	The Contractor keeps the Site clean, orderly and safe throughout the Works and completes final cleaning before Completion.

	S 270 Waste materials
	The Contractor removes waste regularly, lawfully disposes of waste, protects common areas during waste removal, segregates recyclable waste where required and provides disposal certificates where required by the landlord or Project Manager.

	S 280 BBB-EE requirements
	The Contractor complies with all applicable procurement, transformation and B-BBEE requirements stated in the tender documents and Contract Data.



S 300 Contractor’s design

	S 305 Design responsibility

See clause ECC4 21.1
	The Contractor is responsible for developing the final coordinated design from the high-level design information and annexures. The Contractor's design includes all design development, coordination and construction information required for the fit-out and services within its scope. Acceptance of the Contractor's design by the Project Manager, SANEDI or the landlord does not relieve the Contractor of responsibility for the design allocated to it.

	S 310 Design submission procedures and acceptance criteria
See clauses:
ECC4 21.2
	The Contractor submits design information for acceptance in stages, including concept review, developed design, coordinated construction drawings, shop drawings, samples, technical data sheets, method statements and commissioning proposals. The Contractor allows for review periods, resubmissions and reasonable comments from SANEDI, the Project Manager, Supervisor, independent designer, landlord and statutory authorities.

	S 315 Design approvals from Others
	The Contractor obtains or supports all design approvals from Others required for the Works, including landlord approval, landlord-approved contractor review, building management approval, authority approval, fire approval and utility/service provider approvals where applicable. No construction starts until the relevant design is approved by the Client and landlord and accepted by the Project Manager.

	S 320 Client’s design requirements

ECC4 21.2
	The Client's design requirements are stated in the Scope and annexures, including the high-level space planning drawings, BOQ / pricing support document, risk items, HVAC status report, FF&E information pack, landlord requirements, Site Information, ICT interface requirements and technical schedules.

	S 325 Design co-ordination
	The Contractor coordinates architectural, interior, FF&E, electrical, lighting, HVAC, plumbing, fire, security, signage and ICT interface requirements. The Contractor identifies conflicts or gaps in the tender documents and resolves them through the Project Manager before construction.

	S 330 Requirements of Others
	Requirements of Others include the landlord requirements, landlord fit-out rules, access rules, contractor approval rules, statutory approvals, building management procedures, utility provider requirements and the ICT contractor's reasonable interface requirements.

	S 325 Using the Contractor’s design
See clause ECC4 22.1
	The Client may use the Contractor's design information for operating, maintaining, altering, repairing, reinstating, completing and occupying the Works and for future landlord or statutory approval processes, subject to the rights stated in the Contract.

	S 340 Client’s requirements for design of Equipment
ECC4 23.1
	Equipment and FF&E designed or selected by the Contractor are suitable for commercial office use, comply with the FF&E information pack, fit within the approved layout and include warranties, maintenance information and product data.



S 400 Completion

	S 405 Completion definition

ECC4 11.2(2)
	Completion is achieved when the Works are complete, safe, clean, compliant, tested, commissioned, certified, approved for occupation where required, and handed over with all required as-built information, warranties, certificates, O&M manuals, landlord sign-off and SANEDI handover documentation. The Works are not complete if outstanding Defects prevent occupation or following work.

	S 415 Training
	The Contractor trains SANEDI facilities representatives and any nominated users in the operation and maintenance of systems and equipment included in the Contractor's scope, including HVAC controls where applicable, lighting controls, access/security systems, installed FF&E and maintenance requirements.

	S 420 Final clean
	The Contractor carries out a full final clean of the Works, including floors, walls, glass, joinery, FF&E, services outlets, bathrooms/kitchen areas where included, and common areas affected by the Works.

	S 425 Security
	The Contractor hands over all keys, access devices, manuals, asset information and security-related documentation for items within its scope. The Contractor coordinates security interfaces with the landlord and SANEDI.

	S 430 Correcting Defects
	The Contractor corrects Defects in accordance with the Contract and the response times stated in the Scope or Contract Data. Urgent defects affecting safety, access, fire, electrical, water leaks, HVAC operation or occupation are attended to immediately or within the period instructed by the Project Manager.

	S 435 Pre-Completion arrangements
	Before Completion, the Contractor completes snagging, testing, commissioning, certifications, landlord inspection, SANEDI inspection, ICT interface readiness, final cleaning and handover documentation.

	S 440 Use of the works
ECC4 35.2
	The Client may use or occupy the Works only after Completion or taking over under the Contract. Any early access required for SANEDI, the landlord or the ICT contractor is coordinated through the Project Manager.



S 500 Programme

	S 505 Programme requirements

ECC4 31.2
ECC4 31.3
	The programme complies with ECC4 clause 31.2 and shows design development, SANEDI reviews, landlord reviews, statutory approvals, procurement, long-lead items, demolition, fit-out, services, FF&E, ICT contractor interfaces, testing, commissioning, snagging, landlord inspections, handover and Completion. The programme links each Activity Schedule item to programme activities.

	S 510 Methodology statement
	The Contractor submits a methodology statement explaining how it will deliver the turnkey refurbishment, manage landlord approvals, coordinate design development, protect the building, manage access, coordinate with the ICT contractor, control quality and achieve Completion.

	S 515 Work of the Client and Others
ECC4 25.1
ECC4 60.1(5)
	The Contractor allows for work by Others, including SANEDI, the Project Manager, Supervisor, designer, landlord, landlord-approved contractors and SANEDI's separate ICT contractor. ICT works are excluded from the Contractor's scope except for coordination, access, interface and programme obligations.

	S 520 Other information required
	The Contractor provides procurement schedules, design submission schedules, sample registers, approval registers, risk registers, interface registers, commissioning plans, snag lists, handover registers and other information reasonably required by the Project Manager.

	S 525 Revised programme
	The Contractor submits revised programmes at the intervals stated in the Contract Data and whenever required by the Contract. Revised programmes show actual progress, effect of compensation events, changes to approval periods, ICT interface changes and mitigation proposals.



S 600 Quality management

	S 605 Quality management system

ECC4 40.1
	The Contractor operates a quality management system suitable for commercial office refurbishment and fit-out works and provides inspection, testing, sample, approval and handover controls.

	S 610 Quality policy statement and quality plan
	The Contractor submits a quality policy statement and quality plan within the period stated in the Contract Data. The quality plan includes inspection and test plans, hold points, sample approval process, subcontractor controls, defect management and handover controls.

	S 615 Samples
	The Contractor submits samples, swatches, mock-ups and product data for finishes, flooring, paint, partitions, glazing, ceilings, doors, ironmongery, joinery, lighting, signage, manifestation and FF&E where required by the Scope or Project Manager.



S 700 Tests and inspections

	S 705 Tests and inspections

ECC4 41.1
ECC4 41.2
ECC4 42.1
ECC4 60.1(16)
	The Contractor carries out all tests and inspections required by the Scope, laws, standards, landlord requirements, manufacturers and the Project Manager. This includes electrical, HVAC, plumbing, fire, emergency lighting, access/security interfaces, FF&E inspection, final clean and handover inspections.

	S 710 Samples
	Samples are submitted for acceptance before procurement or installation of visible finishes, FF&E and items affecting design quality.

	S 715 Management of tests & inspections and provision of samples
	The Contractor manages tests, inspections and samples using a register showing item, submission date, reviewer, status, comments, resubmission and acceptance.

	S 720 Covering up completed work
	The Contractor does not cover up work until the Supervisor has had a reasonable opportunity to inspect or witness the work where inspection is required.

	S 725 Supervisor’s procedure for inspections and watching tests 
	The Contractor gives the Supervisor adequate notice of tests and inspections. The Supervisor may inspect the Works, materials, samples and off-site fabrication relating to the Works.



S 800 Management of the works 

	S 805 Project team – Others


	Others include SANEDI, the Project Manager, Supervisor, designer, landlord, landlord's representatives, landlord-approved contractors, statutory authorities, utility providers, SANEDI's ICT contractor and building management. The Contractor participates in early warning and coordination meetings to manage interfaces with Others.

	S810 Communication system and reporting

ECC4 13.2
	Microsoft suite or equivalent. Contractor to report fortnightly by providing a comprehensive project report including as a minimum the following:
· HSE
· Security
· Quality
· Progress
· Commercial
· Risk
· Other as applicable
Reports to be submitted in native and pdf format.

	S 815 Management procedures
	The Contractor uses registers for early warnings, communications, submissions, approvals, RFIs, samples, risks, changes, tests, commissioning, handover documentation and snags. Meetings are held weekly unless agreed otherwise.

	S 820 Contractor’s application for payment

ECC4 50.2
	The Contractor's application for payment is submitted in accordance with the Contract and is supported by activity completion evidence, progress records, photographs, test records, delivery notes, handover records and other information required by the Project Manager.




S 900 Working with the Client and Others

	S 905 Sharing the Working Areas with Others

ECC 25.1
ECC 60.1(5)
	The Contractor shares the Working Areas with SANEDI, the Project Manager, Supervisor, designer, landlord representatives, landlord-approved contractors, building management and SANEDI's separate ICT contractor as required. The Contractor allows reasonable access to Others where shown on the accepted programme or instructed by the Project Manager.

	S 910 Co-operation 

ECC 25.1
ECC 60.1(5)
	The Contractor co-operates with SANEDI, the landlord and Others so that approvals, inspections, landlord sign-off, ICT works, testing, commissioning and occupation are achieved without avoidable disruption.

	S 915 Co-ordination 
	The Contractor coordinates work sequences, design information, access, service shutdowns, ceiling access, builders work, power interfaces, FF&E placement and ICT interface requirements with Others.

	S 920 Authorities and utilities providers
	The Contractor obtains or supports approvals from authorities and utilities providers where allocated to the Contractor and provides all technical information required for approvals related to its design and Works.




S 1000 Services and other things to be provided

	S 1005 Services and other things provided by the Contractor for the use by the Client, Project Manager, Supervisor or Others

ECC4 25.2
	The Contractor provides all temporary facilities, tools, equipment, hoardings, protection, waste containers (skips), lighting, signage, storage, permits, access arrangements and other temporary things required for Providing the Works, unless stated otherwise.

	S 1010 Services and other things to be provided by the Client.

ECC4 25.2
	Client provides available information when available; absence or incompleteness of such information does not relieve the Contractor from its assessment, design coordination and turnkey obligations, except where SANEDI expressly instructs a change outside the scope.



S 1100 Health and safety

	S 1105 Health and safety requirements

ECC4 27.4
	The Contractor complies with the Occupational Health and Safety Act, Construction Regulations, landlord safety rules, permit-to-work requirements, SANEDI requirements and all applicable health and safety laws. The Contractor prepares and maintains a project safety file and safe work procedures.

	S 1110 Method statements
	The Contractor submits method statements for demolition, hot works, working at height, electrical isolation, services modifications, waste removal, lifting/moving materials, common area protection, HVAC works, fire system works and any other high-risk activity.

	S 1115 Legal requirements
	The Contractor complies with all applicable legal requirements including building regulations, SANS requirements, OHSA, Construction Regulations, fire requirements, electrical requirements and landlord rules.

	S 1120 Inspections
	The Contractor permits health and safety inspections by SANEDI, the Project Manager, Supervisor, landlord, statutory authorities and their representatives.

	S 1125 Deleterious and hazardous materials
	The Contractor does not use deleterious or hazardous materials. If asbestos, mould, contaminated material or other hazardous material is found, the Contractor stops affected work, makes the area safe and notifies the Project Manager immediately.

	S 1130 Pre-Construction Information
	Pre-construction health and safety information includes Site Information, landlord requirements, access restrictions, known risks, existing condition information, previous surveys, statutory requirements and the Contractor's risk assessments.



S 1200 Subcontracting

	S 1205 Restrictions or requirements for subcontracting
	Subcontractors for HVAC, electrical, fire, plumbing, access control, security, signage, glazing, FF&E and any landlord-controlled systems are subject to Project Manager acceptance and landlord approval where required. The Contractor remains responsible for subcontractor performance.

	S 1210 Acceptance procedures

ECC4 C, D, E 11.2(26)
ECC4 F 11.2(27)
	The Contractor submits proposed subcontractor names, scope, qualifications, registrations, insurances, experience and landlord approval status for acceptance before appointment where required.



S 1300 Title

	S 1305 Marking

ECC4 71.1
	The Contractor marks Plant and Materials as required for identification, delivery, storage, handover, warranties and asset schedules.

	S 1310 Materials from excavation and demolition

ECC4 73.2
	Materials arising from demolition become the Contractor's property for lawful disposal unless the Project Manager identifies items to be retained by SANEDI or the landlord. Retained items are protected, labelled and handed over as instructed.



S 2000 Performance bond (Option X13)

	S 2005 Form of the performance bond

ECC4 X13.1
	The form of performance bond is included in Part C1.3 if secondary Option X13 is selected. The amount is stated in the Contract Data.



S 2700 Client’s work specifications

	S 2705 Client’s work specifications
	The Client's work specifications include the following annexures, which form part of the Scope where stated:
· SANEDI BOQ live Excel, 
· SANEDI FF&E Schedule, 
· SANEDI CAD DWG, 
· SANEDI PDF Drawing Pack, 
· landlord code/conduct, fire report/details, 



S 2800 Client’s drawings

	S 2805 Drawings
	Drawings are listed in Annexure A and include the high-level space planning and design drawings prepared for tender. The Contractor develops final coordinated construction drawings for acceptance by the Project Manager and approval by SANEDI and the landlord before construction.






[bookmark: _Toc67397035]C3.2:  Scope provided by the Contractor for its design.
The Contractor provides with its tender a preliminary design development approach, proposed key design personnel, proposed subcontractors and a programme showing how final design is developed and approved before construction.
After the Contract Date, the Contractor provides the Scope for its design comprising final coordinated drawings, shop drawings, technical schedules, samples, product data, method statements, design calculations where applicable, and submissions required for landlord and statutory approvals.
The Contractor's design submissions must address the high-level plans, BOQ/pricing support document, risk items, HVAC status report, FF&E information pack, landlord requirements, ICT interface requirements and technical schedules.
ICT design and active ICT equipment are excluded, except that the Contractor coordinates with SANEDI's ICT contractor and includes ICT interface requirements in its programme and construction sequencing.
No construction or service alteration starts until the relevant design package is accepted by the Project Manager and approved by SANEDI, landlord/building management and authorities/specialists where required.







[bookmark: _Toc67397036]Part C4 Site Information

SI 100 Site location

	SI 105 Site location
	The Site is SANEDI's leased office floor at Upper Grayston Block B, 150 Linden Road, Sandton, Johannesburg, including only the refurbishment area, balcony and ancillary areas expressly identified in the Scope and landlord-approved fit-out boundary. The floor has not been in operational use by SANEDI. The contractor must verify existing services and systems during site inspection/post-award assessments, especially HVAC, fresh air, fire, electrical and plumbing



SI 200 Reports and surveys

	SI 205 Reports and surveys
	Reports and surveys to be included or provided as Site Information include the high-level plans, available lease/addendum information relevant to the Site, available condition information, HVAC status report (if available), landlord requirements, available as-built drawings and any previous surveys or previous refurbishment information provided by SANEDI or the landlord. Tenderers must inspect the Site and raise queries during the tender clarification period.



SI 300 Public information

	SI 305 Public information
	Public information includes the building address, landlord/building management access procedures, statutory requirements applicable to commercial office refurbishment and public authority requirements identified in the tender documents. No reliance is placed on information not included in the Contract unless accepted by the Project Manager.



SI 400 Buried pipes, services and other objects

	SI 405 Buried pipes, services and other objects
	Available information on existing services, hidden services and other objects is limited to information provided in the Site Information and annexures. Existing services may include HVAC, electrical, lighting, fire detection, sprinkler/fire protection, plumbing, access control and data/ICT pathways. The Contractor verifies visible services before work and obtains approval before isolating, removing, relocating or penetrating services.



SI 500 Buildings, structures and other things adjacent to the Site

	SI 505 Buildings, structures and other things adjacent to the Site
	The Site is located in a leased commercial building with common areas, lift lobbies, stairs, access routes, parking, services, landlord-controlled systems and possible adjacent tenants. The Contractor protects all buildings, structures, common areas and other things adjacent to the Site and complies with landlord requirements.

The ground floor of the building is occupied by a wellness centre and medical practice. The Contractor should expect that noise, vibration, dust, access restrictions and disruptive works may be sensitive due to the nature of the ground floor operations. The landlord will discuss noisy/disruptive work arrangements with the wellness centre, and Contractor must allow for restricted working times and show these in its programme.



SI 600 Health and safety information

	
	Known health and safety information includes working in an existing leased commercial building, access and security controls, common area protection, potential live services, demolition and strip-out activities, waste removal, working at height, electrical isolation, fire system interfaces, HVAC works, hot works and coordination with Others.
The Contractor prepares its own risk assessments and method statements and verifies all Site conditions before starting work.
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